## Account Structure Mapping
MEDICA Electronic Eligibility Questionnaire
Customer: | [6 empty] | Plan Effective Date:
Sunrise Banks | [6 empty] | 2022-01-01
Plan Information (2000 Loop – REF Segment – Member Policy Number) | [5 empty] | Class Codes (2300 Loop – REF 17 Segment )
Plan Name | DIV | Group # | Loop 2000 REF*1L | Ded code | Ben Option | Description | Class Code | Ben Option
MIC PP 2000-10% | MTK | 44695 | MTK44695 | MTRAD | EEPP, EEFPP, EE1PP | EMPLOYEE | 01 | EEPP, EEVPL
MIC VPL 2000-10% | MTK | 44696 | MTK44696 | MTRAD | EEVPL, EE1VPL, EEFVPL | EMPLOYEE+1 | 02 | EE1PP, EE1VPL
MIC PP 2000-0%-Single | MTK | 44697 | MTK44697 | M2HD | EEPP | FAMILY | 04 | EEFPP, EEFVPL
MIC PP 2000-0%-Family | MTK | 44698 | MTK44698 | M2HD | EEFPP, EE1PP
MIC VPL 2000-0%-Single | MTK | 44699 | MTK44699 | M2HD | EEVPL
MIC VPL 2000-0%-Family | MTK | 44700 | MTK44700 | M2HD | EE1VPL, EEFVPL
MIC PP 5500-0% H.S.A. | MTK | 44701 | MTK44701 | M55HD | EEPP, EEFPP, EE1PP
MIC VPL 5500-0% H.S.A. | MTK | 44702 | MTK44702 | M55HD | EEVPL, EE1VPL, EEFVPL
Plans | Ded code | Benefit Option
2000-10% | MTRAD | Employee Only PP | EEPP
|  | Employee + Family PP | EEFPP
|  | Employee + 1 PP | EE1PP
|  | Employee Only VPL | EEVPL
|  | Employee + 1 VPL | EE1VPL
|  | Emp + Family VPL | EEFVPL
2000-0% | M2HD | Employee Only PP | EEPP
|  | Employee + Family PP | EEFPP
|  | Employee + 1 PP | EE1PP
|  | Employee Only VPL | EEVPL
|  | Employee + 1 VPL | EE1VPL
|  | Emp + Family VPL | EEFVPL
5500-0% | M55HD | Employee Only PP | EEPP
|  | Employee + Family PP | EEFPP
|  | Employee + 1 PP | EE1PP
|  | Employee Only VPL | EEVPL
|  | Employee + 1 VPL | EE1VPL
|  | Emp + Family VPL | EEFVPL

## ACCOUNT INFO & STRUCTURE
MEDICA Electronic Eligibility Questionnaire
Customer: | [6 empty] | Plan Effective Date: |  | Submission ID (REF02 of Header Loop):
Sunrise Banks | [6 empty] | 2022-01-01
Plan Information (2000 Loop – REF Segment – Member Policy Number) | [6 empty] | Departments (2000 Loop – REF Segment ) |  | Class Codes (2300 Loop – REF Segment )
Plan Name | DIV | Group # | IND | FAM | PCC'S | ACO? | Dept Description | Dept Number | Description | Class Code
MIC PP 2000-10% | MTK | 44695 | [6 empty] | EMPLOYEE | 01
MIC VPL 2000-10% | MTK | 44696 | [6 empty] | FAMILY | 04
MIC PP 2000-0%-Single | MTK | 44697 | [6 empty] | D-SPLIT FAMILY | 10
MIC PP 2000-0%-Family | MTK | 44698 | [6 empty] | COBRA EE | 29
MIC VPL 2000-0%-Single | MTK | 44699 | [6 empty] | COBRA FAMILY | 32
MIC VPL 2000-0%-Family | MTK | 44700 | [6 empty] | COBRA EX-SP | 33
MIC PP 5500-0% H.S.A. | MTK | 44701 | [6 empty] | EMPLOYEE | 01
MIC VPL 5500-0% H.S.A. | MTK | 44702 | [6 empty] | EMPLOYEE+1 | 02
[9 empty] | FAMILY | 04
[9 empty] | D-SPLIT FAMILY | 10
[9 empty] | D-SPLIT EMPLOYEE +1 | 11
[9 empty] | COBRA EE | 29
[9 empty] | COBRA EE+1 | 30
[9 empty] | COBRA FAMILY | 32
[9 empty] | COBRA EX-SP | 33
[9 empty] | EMPLOYEE | 01
[9 empty] | EMPLOYEE+SPOUSE | 02
[9 empty] | EMPLOYEE+CHILD(REN) | 03
[9 empty] | FAMILY | 04
[9 empty] | D-SPLIT FAMILY | 10
[9 empty] | D-SPLIT EMPLOYEE+SPOUSE | 11
[9 empty] | COBRA EE | 29
[9 empty] | COBRA EE+SP | 30
[9 empty] | COBRA EE+CH(REN) | 31
[9 empty] | COBRA FAMILY | 32
[9 empty] | COBRA EX-SP | 33
Any change to previous structure information will be idenfitied in red

## FILE INFO
EDI FILE INFORMATION |  | Notes:
Funding Type
Start Date Guidelines
Term Date Guidelines
COBRA/Retirees on File?
Employee Count
Dependent (SP, CH) Count
New Start Dates for Date Sensitive Field?
Term Dates passed for Plan Change?
Term Dates passed Once?
SSN's provided for All?
PCC Handling
QMCSO Handling (DEPENDENTS UNDER 12)
File Format
Full or Changes
Frequency / Day
Submission Method
Vendor and/or HRIS System | UKG

## Contact Information
Vendor | Customer | Medica
Pre-Implementation Analyst Name | Client Contact (Group Administrator) | Account Manager
TBD | Karie Larson | Jill Berg
Phone | Phone | Phone
| 651-259-2268 | 952-992-3790
Email | Email | Email
| karie.larson@sunrisebanks.com | jill.berg@medica.com
Post-Implementation Analyst Name | Weekly EDI Contact | Electronic Eligibility Analyst
Karie Larson
Phone | Phone | Phone
651-259-2268
Email | Email | Email
Karie.larson@sunrisebanks.com
Pre-Implementation Technical Contact | Weekly EDI Contact
Phone | Phone
Email | Email
Post-Implementation Technical Contact
Phone
Email

## New File Setup Timeline
Milestone |  | Timeline | Goal Dates*
1 | Questionnaire completed by Customer/AM and provided to assigned EEA. | Process initiates. | 2021-09-03
2 | Conference call with customer and/or vendor to review questionnaire/layout. | Within 7 days after receipt of questionnaire. | 2021-09-10
3 | SFTP setup request. Note: Process cannot start without SFTP contact | Day of the call or within 2 days after call if SFTP contact needs to be assigned. | 2021-09-12
4 | Follow-up from conference call responded to. | Within 5 days of conference call. | 2021-09-15
5 | SFTP setup complete. | Within 14 days of SFTP setup request. | 2021-09-26
6 | Initial test file. | First test file is expected 21 days after conference call. | 2021-10-01
7 | Response from Medica to customer and/or vendor. | Within 5 business days after receipt of test file. | 2021-10-06
8 | Response from customer and/or vendor to Medica. | Within 5 business days from receipt of test file results. | 2021-10-11
9 | Subsequent test file. | If needed, subsequent test files should come within 5 days of getting test results. | 2021-10-16
10 | Response from Medica to customer and/or vendor. | Within 5 business days after receipt of test file. | 2021-10-21
11 | Response from customer and/or vendor to Medica. | Within 5 business days from receipt of test file results. Further test files will go back to step 9 and adjust the date. | 2021-10-26
12 | Final signoff. | Within 24 hours of satisfactory test results. | 2021-10-27
13 | Production file. | When testing is satisfactorily complete, production file should come within 5 business days . | 2021-11-01
*Once in production, former enrollment process (sending paper enrollments or updating eServices) should cease
*Dates that fall on a weekend will go to the following Monday
*Actual dates will be populated upon assignment of an Electronic Eligibility Analyst
Formulas:
Goal Dates* = [Goal Dates*, row above]+7

## Renewal
Open Enrollment Questionnaire |  | Notes:
1 | Renewal Date:
2 | When is your Open Enrollment election period?
Start:
Stop:
3 | Will there be any group number changes (adding or terminating plans)?
4 | Will there be any changes to the following fields:
5 | Will PCC changes be sent on the Open Enrollment file?
6 | Will there be a significant change in membership on the OE file?
7 | How will plan year effective dates be sent on the OE file?
8 | Will you be submitting terminations on the file or will we term by omission?
9 | Will you be sending an OE test file? If so, please specify the date.
Standard TAT for testing files is 5 business days. Please keep in mind, multiple test files may be needed. We recommend sending your first test file at least 3 weeks prior to your scheduled OE file.
10 | When will the OE file be sent to Medica?
Validated OE files will be processed and results sent by the 5th business day. To ensure all enrollees receive ID cards by the effective date, the OE file should be sent to Medica no later than the first Friday of the month prior to the renewal month.
11 | Will you continue to send files throughout the remainder of the current plan year, or will they be paused?
Once we receive new plan year effective dates, all eligibility updates prior to the new plan year must be processed manually.
1/1/2022

## HIPAA Specs
HEADER LOOP – REF SEGMENT - SUBMISSION ID
SEG ID | ELEMENT ID | ELEMENT VALUES
REF | 01 | 38
REF | 02 | SUNBANKF
2000 LOOP – REF SEGMENT - MEMBER POLICY NUMBER
SEG ID | ELEMENT ID | ELEMENT VALUES
REF | 01 | 1L
REF | 02 | DIV and 5-DIGIT GROUP NUMBER
2000 LOOP – REF SEGMENT - COURT ORDERED/QMCSO MEMBERS
SEG ID | ELEMENT ID | ELEMENT VALUES
REF | 01 | ZZ
REF | 02 | Q | likely won't send
2300 LOOP – REF SEGMENT - CLASS CODES
SEG ID | ELEMENT ID | ELEMENT VALUES
REF | 01 | 17
REF | 02 | 2 DIGIT CLASS CODE | benefit option